9th November 2010

Request for Proposal

Dear Sir/Madam,

Subject:  RFP FOR THE CONSULTANCY FOR THE PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS Reference:No.00050470UGA/10/071/GEN

You are requested to submit a proposal for the PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS based on the enclosed Terms of Reference (TOR).

- To enable you to submit a proposal, attached are:

Acknowledgment Letter

  - Instructions to Offerors………………………………..(Annex I)

  - General Conditions of Contract………………………..(Annex II)

  - Terms of Reference (TOR)…………………………….(Annex III)

  - Proposal Submission Forms……………………………(Annex IV)

  - Price Schedule………………………………………….(Annex V)

- Your offer comprising of technical proposal and financial proposal, in separate sealed envelopes, should reach the following address no later than 4:00 PM, 24th November 2010.

The Resident Representative,

United Nations Development Programme (UNDP)

Plot 15B Clement Hill Road, Ruth Towers

P. O. Box 7184

Kampala, Uganda

And marked with –

“RFP: CONSULTANCY FOR THE PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS”

- If you request additional information, we will endeavour to provide information

Expeditiously, but any delay in providing such information will not be considered a reason for extending the submission date of your proposal.

ACKNOWLEDGEMENT LETTER

(To be submitted on or before 17th November 2010)

Date:_____________

Dear Sir/Madam,

## Subject:  RFP: CONSULTANCY FOR THE PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS

We, the undersigned, acknowledged receipt of your Request for Proposal dated 9th November 2010 and, hereby confirm that:

(   )  we intend					(   ) we do not intend

to submit a proposal to UNDP by the deadline by 4.00 p.m. on 24th November 2010.

Name of Authorized

Representative			: ____________________________________

Signature			: ____________________________________

Title				: ____________________________________

Name of Organization		: ____________________________________

If you are in the required field but do not intend to submit a proposal to UNDP, please indicate the reason:

(   )	We do not have the capacity to submit a proposal

(   )	We cannot meet the technical requirement for this RFP

(   )	We do not think we can make a competitive offer at this time.

(   )	Others: (Please specify___________________________________________ )

### Please return this acknowledgement letter immediately via e mail to: adenike.akoh@undp.org.

Annex 1

Instructions of Offerors

# Introduction

- General

Purpose of the RFP is for the PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS

2.	Cost of Proposal

The offeror shall bear all costs associated with the preparation and submission of the proposal, the UNDP will in no case be responsible or liable for those costs, regardless of the conduct of outcome of the solicitation.

B.      Solicitation Documents

3.	Contents of solicitation documents

Proposals must offer services for the total requirement.  Proposals offering only part of the requirement will be rejected.  The offeror is expected to examine all corresponding instructions, forms, terms and specifications contained in the solicitation documents.  Failure to comply with the documents will be at the offeror’s risk and may affect the evaluation of the proposal.

4.	Clarification of solicitation documents

A prospective Offeror requiring any clarification of the Solicitation Documents may notify the procuring UNDP entity in writing at the organization’s mailing address or fax number indicated in the RFP. The procuring UNDP entity will respond in writing to any request for clarification of the Solicitation Documents that it receives earlier than two weeks prior to the deadline for the submission of Proposals. Written copies of the organization’s response (including an explanation of the query but without identifying the source of inquiry) will be published in the country office website under the frequently asked questions.

5.	Amendments of solicitation documents

At any time prior to the deadline for submission of Proposals, the procuring UNDP entity may, for any reason, whether at its own initiative or in response to a clarification requested by a prospective Offeror, modify the Solicitation Documents by amendment. All prospective Offerors that have received the Solicitation Documents will be notified in writing of all amendments to the Solicitation Documents. In order to afford prospective Offerors reasonable time in which to take the amendments into account in preparing their offers, the procuring UNDP entity may, at its discretion, extend the deadline for the submission of Proposals.

C.	Preparation of Proposals

6.	Language of the proposal

The Proposals prepared by the Offeror and all correspondence and documents relating to the Proposal exchanged by the Offeror and the procuring UNDP entity shall be written in the English language. Any printed literature furnished by the Offeror may be written in another language so long as accompanied by an English translation of its pertinent passages in which case, for purposes of interpretation of the Proposal, the English translation shall govern.

7.	 Documents comprising the proposal

The Proposal shall comprise the following components:

(a)	Proposal submission form;

(b)	Operational and technical part of the Proposal, including documentation to demonstrate that the Offeror meets all requirements;

(c)	Price schedule, completed in accordance with clauses 8 and 9;

8.	Proposal form

The Offeror shall structure the operational and technical part of its Proposal as follows:

(a)	Management plan

This section should provide corporate orientation to include the year and state/country of incorporation and a brief description of the Offeror’s present activities. It should focus on services related to the Proposal.

This section should also describe the organizational unit(s) that will become responsible for the contract, and the general management approach towards a project of this kind. The Offeror should comment on its experience in similar projects and identify the person(s) representing the Offeror in any future dealing with the procuring UNDP entity.

(b)	Resource plan

This should fully explain the Offeror’s resources in terms of personnel and facilities necessary for the performance of this requirement. It should describe the Offeror’s current capabilities/facilities and any plans for their expansion.

(c)	Proposed methodology

This section should demonstrate the Offeror’s responsiveness to the specification by identifying the specific components proposed, addressing the requirements, as specified, point by point; providing a detailed description of the essential performance characteristics proposed warranty; and demonstrating how the proposed methodology meets or exceeds the specifications. The operational and technical part of the Proposal should not contain any pricing information whatsoever on the services offered. Pricing information shall be separated and only contained in the appropriate Price Schedules.  Information which the Offeror considers proprietary, if any, should be clearly marked “proprietary” next to the relevant part of the text and it will then be treated as such accordingly.

Proposal prices:

The Offeror shall indicate on an appropriate Price Schedule, an example of which is contained in these Solicitation Documents, the prices of services it proposes to supply under the contract.

10.	Proposal currencies

All prices shall be quoted in US dollars but will be converted and paid at prevailing UN Exchange rate for companies based in Uganda.

11.	Period of validity of proposals

Proposals shall remain valid for sixty (60) days after the date of Proposal submission prescribed by the procuring UNDP entity, pursuant to the deadline clause. A Proposal valid for a shorter period may be rejected by the procuring UNDP entity on the grounds that it is non-responsive. In exceptional circumstances, the procuring UNDP entity may solicit the Offeror’s consent to an extension of the period of validity. The request and the responses thereto shall be made in writing. An Offeror granting the request will not be required nor permitted to modify its Proposal.

12.	Format and signing of proposals

The Offeror shall prepare two copies of the Proposal, clearly marking each “Original Proposal” and “Copy of Proposal” as appropriate. In the event of any discrepancy between them, the original shall govern. The two copies of the Proposal shall be typed or written in indelible ink and shall be signed by the Offeror or a person or persons duly authorized to bind the Offeror to the contract. The latter authorization shall be indicated by written power-of-attorney accompanying the Proposal. A Proposal shall contain no interlineations, erasures, or overwriting except, as necessary to correct errors made by the Offeror, in which case such corrections shall be initialed by the person or persons signing the Proposal.

13.	Payment

UNDP shall effect payments to the Contractor after acceptance by the procuring UNDP entity of the invoices submitted by the contractor, upon achievement of the corresponding milestones.

D.	Submission of Proposals

14.	Sealing and marking of proposals

The Offeror shall seal the Proposal in one outer and two inner envelopes, as detailed below.

(a) The outer envelope shall be addressed to:

The Resident Representative

United Nations Development Programme (UNDP)

Plot 24 Prince Charles Drive, Kololo

P.O. Box 7184

Kampala, Uganda

Attn: “Procurement Unit”

and, marked with – “RFP: CONSULTANCY FOR THE PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS”

(b) Both inner envelopes shall indicate the name and address of the Offeror. The first inner envelope shall contain the information specified in Clause 8 (Proposal form) above, with the copies duly marked “Original” and “Copy”. The second inner envelope shall include the price schedule only, duly identified as such. The second inner envelope shall contain the technical proposal and the financial proposal in separate sealed envelopes. Note, that the proposal will be disqualified if the financial (cost) is not separated from the technical proposal and if the inner envelopes are not sealed and marked as per the instructions in this clause, UNDP will not assume responsibility for the Proposal’s misplacement or premature opening.

15.	Deadline for submission of proposals

Proposals must be received by UNDP at the address specified under clause Sealing and marking of Proposals no later than 4:00 pm, 24th November 2010.

UNDP may, at its own discretion extend this deadline for the submission of Proposals by amending the solicitation documents in accordance with clause Amendments of Solicitation Documents, in which case all rights and obligations of the procuring UNDP entity and Offerors previously subject to the deadline will thereafter be subject to the deadline as extended.

16.	Late Proposals

Any Proposal received by the procuring UNDP entity after the deadline for submission of proposals, pursuant to clause Deadline for the submission of proposals, will be rejected.

17.	Modification and withdrawal of Proposals

The Offeror may withdraw its Proposal after the Proposal’s submission, provided that written notice of the withdrawal is received by the procuring UNDP entity prior to the deadline prescribed for submission of Proposals. The Offeror’s withdrawal notice shall be prepared, sealed, marked, and dispatched in accordance with the provisions of clause Deadline for Submission of Proposals. The withdrawal notice may also be sent by telex or fax but followed by a signed confirmation copy.

No Proposal may be modified subsequent to the deadline for submission of proposals. No Proposal may be withdrawn in the interval between the deadline for submission of proposals and the expiration of the period of proposal validity specified by the Offeror on the Proposal Submission Form.

E.	Opening and Evaluation of Proposals

18.	Opening of proposals

The procuring UNDP entity will open the Proposals in the presence of a Committee formed by the Head of the procuring UNDP entity.

19.	Clarification of proposals

To assist in the examination, evaluation and comparison of Proposals, the Purchaser may at its discretion, ask the Offeror for clarification of its Proposal. The request for clarification and the response shall be in writing and no change in price or substance of the Proposal shall be sought, offered or permitted.

20.	Preliminary examination

The Purchaser will examine the Proposals to determine whether they are complete, whether any computational errors have been made, whether the documents have been properly signed, and whether the Proposals are generally in order. Arithmetical errors will be rectified on the following basis: If there is a discrepancy between the unit price and the total price that is obtained by multiplying the unit price and quantity, the unit price shall prevail and the total price shall be corrected. If the Offeror does not accept the correction of errors, its Proposal will be rejected. If there is a discrepancy between words and figures the amount in words will prevail. Prior to the detailed evaluation, the Purchaser will determine the substantial responsiveness of each Proposal to the Request for Proposals (RFP). For purposes of these Clauses, a substantially responsive Proposal is one which conforms to all the terms and conditions of the RFP without material deviations. The Purchaser’s determination of a Proposal’s responsiveness is based on the contents of the Proposal itself without recourse to extrinsic evidence.

A Proposal determined as not substantially responsive will be rejected by the Purchaser and may not subsequently be made responsive by the Offeror by correction of the nonconformity.

21.	Evaluation and comparison of proposals

A two-stage procedure is utilized in evaluating the proposals, with evaluation of the technical proposal being completed prior to any price proposal being opened and compared. The price proposal of the proposals will be opened only for submissions that passed the minimum technical score of 70% of the obtainable score of 1000 points in the evaluation of the technical proposals. The technical proposal is evaluated on the basis of its responsiveness to the Term of Reference (TOR). In the Second Stage, the price proposal of all contractors, who have attained minimum 70% score in the technical evaluation, will be compared. The contract will be awarded to the Contractor offering the lowest price.

Technical Evaluation Criteria

| Summary of Technical Proposal Evaluation Forms |  | Score Weight | Points Obtainable | Company/Other entity |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | A |  | B |  | C |  | D |  | E |
| 1 | Expertise of Firm/ Organisation submitting proposal | 30% | 300 |  |  |  |  |  |  |  |  |  |
| 2 | Proposed work plan and approach | 40% | 400 |  |  |  |  |  |  |  |  |  |
| 3 | Personnel | 30% | 300 |  |  |  |  |  |  |  |  |  |
|  | Total |  | 1000 |  |  |  |  |  |  |  |  |  |

Evaluation forms for technical proposals follow on the next two pages. The obtainable

number of points specified for each evaluation criterion indicates the relative significance

or weight of the item in the overall evaluation process. The Technical Proposal

Evaluation Forms are:

Form 1: Expertise of Firm / Organization Submitting Proposal

Form 2: Proposed Work Plan and Approach

Form 3: Personnel

Note: The score weights and points obtainable in the evaluation sheet are tentative and

should be changed depending on the need or major attributes of technical proposal.

| Technical Proposal Evaluation Form 1 |  |  | Points obtainable | Company / Other Entity |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | A | B | C | D | E |
| Expertise of firm / organisation submitting proposal |  |  |  |  |  |  |  |  |
| 1.1 | Reputation of Organisation and Staff (Competence / Reliability) Company profile, audited financial accounts for the past three years are to be provided. |  | 60 |  |  |  |  |  |
| 1.2 | Litigation and Arbitration history to be provided. ( If there is none, it should also be indicated in the proposal) |  | 15 |  |  |  |  |  |
| 1.3 | General Organisational Capability which is likely to affect implementation (i.e. loose consortium, holding company or one firm, size of the firm / organisation, strength of project management support e.g. project financing capacity and project management controls) |  | 35 |  |  |  |  |  |
| 1.4 | Extent to which any work would be subcontracted (subcontracting carries additional risks which may affect project implementation, but properly done it offers a chance to access specialised skills. |  | 15 |  |  |  |  |  |
| 1.5 | Quality assurance procedures, warranty, certifications and relevant licenses to be provided |  | 45 |  |  |  |  |  |
| 1.6 | Relevance of: - Specialised Knowledge - Experience on Similar Programme / Projects - Experience on Projects in the Region Work for UNDP/ major multilateral/ or bilateral programmes |  | 130 |  |  |  |  |  |
|  |  |  | 300 |  |  |  |  |  |
| Technical Proposal Evaluation Form 2 |  | Points Obtainable |  | Company / Other Entity |  |  |  |  |
|  |  |  |  | A | B | C | D | E |
| Proposed Work Plan and Approach |  |  |  |  |  |  |  |  |
| 2.1 | To what degree does the Offeror understand the task? |  | 50 |  |  |  |  |  |
| 2.2 | Have the important aspects of the task been addressed in sufficient detail? |  | 35 |  |  |  |  |  |
| 2.3 | Are the different components of the project adequately weighted relative to one another? |  | 40 |  |  |  |  |  |
| 2.4 | Is the proposal based on a survey of the project environment and was this data input properly used in the preparation of the proposal? |  | 60 |  |  |  |  |  |
| 2.5 | Is the conceptual framework adopted appropriate for the task? |  | 65 |  |  |  |  |  |
| 2.6 | Is the scope of task well defined and does it correspond to the TOR? |  | 100 |  |  |  |  |  |
| 2.7 | Is the presentation clear and is the sequence of activities and the planning logical, realistic and promise efficient implementation to the project? |  | 50 |  |  |  |  |  |
|  |  |  | 400 |  |  |  |  |  |

| Technical Proposal Evaluation Form 3 |  |  |  | Points Obtainable |  | Company / Other Entity |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | A | B | C | D | E |
| 3.1 | Small Arms Control Expert (CVs of all Key Personnel to be provided) |  |  | 100 |  |  |  |  |  |  |
|  |  |  | Sub-Score |  |  |  |  |  |  |  |
|  | General Qualification |  | 90 |  |  |  |  |  |  |  |
|  | Suitability for the Project |  |  |  |  |  |  |  |  |  |
|  | - International Experience | 20 |  |  |  |  |  |  |  |  |
|  | - Professional Experience in the area of specialisation | 60 |  |  |  |  |  |  |  |  |
|  | - Knowledge of the region | 10 |  |  |  |  |  |  |  |  |
|  | - Language Qualifications |  | 10 |  |  |  |  |  |  |  |
|  |  |  | 100 |  |  |  |  |  |  |  |
| 3.2 | Conflict resolution/Peace building Expert (CV to be provided) |  |  |  | 100 |  |  |  |  |  |
|  |  |  | Sub-Score |  |  |  |  |  |  |  |
|  | General Qualification |  | 90 |  |  |  |  |  |  |  |
|  | Suitability for the Project |  |  |  |  |  |  |  |  |  |
|  | - International Experience | 20 |  |  |  |  |  |  |  |  |
|  | - Professional Experience in the area of specialisation | 60 |  |  |  |  |  |  |  |  |
|  | - Knowledge of the region | 10 |  |  |  |  |  |  |  |  |
|  | - Language Qualifications |  | 10 |  |  |  |  |  |  |  |
|  |  |  | 100 |  |  |  |  |  |  |  |
| 3.3 | Human Rights/Gender expert - with experience in post conflict programming (CV to be provided) |  |  |  | 100 |  |  |  |  |  |
|  |  |  | Sub-Score |  |  |  |  |  |  |  |
|  | General Qualification |  | 90 |  |  |  |  |  |  |  |
|  | Suitability for the Project |  |  |  |  |  |  |  |  |  |
|  | - International Experience | 20 |  |  |  |  |  |  |  |  |
|  | - Professional Experience in the area of specialisation | 60 |  |  |  |  |  |  |  |  |
|  | - Knowledge of the region | 10 |  |  |  |  |  |  |  |  |
|  | - Language Qualification |  | 10 |  |  |  |  |  |  |  |
|  |  |  | 100 |  |  |  |  |  |  |  |
|  | ##### Total Part 3 |  |  |  | 300 |  |  |  |  |  |

F.	Award of Contract

22.	Award criteria, award of contract

The procuring UNDP entity reserves the right to accept or reject any Proposal, and to annul the solicitation process and reject all Proposals at any time prior to award of contract, without thereby incurring any liability to the affected Offeror or any obligation to inform the affected Offeror or Offerors of the grounds for the Purchaser’s action

Prior to expiration of the period of proposal validity, the procuring UNDP entity will award the contract to the qualified Offeror whose Proposal after being evaluated is considered to be the most responsive to the needs of the organisation and activity concerned.

23.	Purchaser’s right to vary requirements at time of award

The Purchaser reserves the right at the time of award of contract to vary the quantity of services and goods specified in the RFP without any change in price or other terms and conditions.

24.	Signing of the contract

Within 30 days of receipt of the contract the successful Offeror shall sign and date the contract and return it to the Purchaser.

Annex II

General Conditions of Contract

1.	LEGAL STATUS

The Contractor shall be considered as having the legal status of an independent contractor vis-à-vis UNDP. The Contractor's personnel and sub-contractors shall not be considered in any respect as being the employees or agents of UNDP or the United Nations.

2.	SOURCE OF INSTRUCTIONS

The Contractor shall neither seek nor accept instructions from any authority external to UNDP in connection with the performance of its services under this Contract. The Contractor shall refrain from any action which may adversely affect UNDP or the United Nations and shall fulfill its commitments with the fullest regard to the interests of UNDP.

3.	CONTRACTOR'S RESPONSIBILITY FOR EMPLOYEES

The Contractor shall be responsible for the professional and technical competence of its employees and will select, for work under this Contract, reliable individuals who will perform effectively in the implementation of this Contract, respect the local customs, and conform to a high standard of moral and ethical conduct.

4.	ASSIGNMENT

The Contractor shall not assign, transfer, pledge or make other disposition of this Contract or any part thereof, or any of the Contractor's rights, claims or obligations under this Contract except with the prior written consent of UNDP.

5.	SUB-CONTRACTING

In the event the Contractor requires the services of sub-contractors, the Contractor shall obtain the prior written approval and clearance of UNDP for all sub-contractors. The approval of UNDP of a sub-contractor shall not relieve the Contractor of any of its obligations under this Contract. The terms of any sub-contract shall be subject to and conform to the provisions of this Contract.

6.	OFFICIALS NOT TO BENEFIT

The Contractor warrants that no official of UNDP or the United Nations has received or will be offered by the Contractor any direct or indirect benefit arising from this Contract or the award thereof. The Contractor agrees that breach of this provision is a breach of an essential term of this Contract.

7.	INDEMNIFICATION

The Contractor shall indemnify, hold and save harmless, and defend, at its own expense, UNDP, its officials, agents, servants and employees from and against all suits, claims, demands, and liability of any nature or kind, including their costs and expenses, arising out of acts or omissions of the Contractor, or the Contractor's employees, officers, agents or sub-contractors, in the performance of this Contract. This provision shall extend, inter alia, to claims and liability in the nature of workmen's compensation, products liability and liability arising out of the use of patented inventions or devices, copyrighted material or other intellectual property by the Contractor, its employees, officers, agents, servants or sub-contractors. The obligations under this Article do not lapse upon termination of this Contract.

8.	INSURANCE AND LIABILITIES TO THIRD PARTIES

8.1	The Contractor shall provide and thereafter maintain insurance against all risks in respect of its property and any equipment used for the execution of this Contract.

8.2	The Contractor shall provide and thereafter maintain all appropriate workmen's compensation insurance, or its equivalent, with respect to its employees to cover claims for personal injury or death in connection with this Contract.

8.3	The Contractor shall also provide and thereafter maintain liability insurance in an adequate amount to cover third party claims for death or bodily injury, or loss of or damage to property, arising from or in connection with the provision of services under this Contract or the operation of any vehicles, boats, airplanes or other equipment owned or leased by the Contractor or its agents, servants, employees or sub-contractors performing work or services in connection with this Contract.

8.4	Except for the workmen's compensation insurance, the insurance policies under this Article shall:

(i)	Name UNDP as additional insured;

(ii)	Include a waiver of subrogation of the Contractor's rights to the insurance carrier against UNDP;

(iii)	Provide that UNDP shall receive thirty (30) days written notice from the insurers prior to any cancellation or change of coverage.

8.5	The Contractor shall, upon request, provide UNDP with satisfactory evidence of the insurance required under this Article.

9.	ENCUMBRANCES/LIENS

The Contractor shall not cause or permit any lien, attachment or other encumbrance by any person to be placed on file or to remain on file in any public office or on file with UNDP against any monies due or to become due for any work done or materials furnished under this Contract, or by reason of any other claim or demand against the Contractor.

10.	TITLE TO EQUIPMENT

Title to any equipment and supplies that may be furnished by UNDP shall rest with UNDP and any such equipment shall be returned to UNDP at the conclusion of this Contract or when no longer needed by the Contractor. Such equipment, when returned to UNDP, shall be in the same condition as when delivered to the Contractor, subject to normal wear and tear. The Contractor shall be liable to compensate UNDP for equipment determined to be damaged or degraded beyond normal wear and tear.

11.	COPYRIGHT, PATENTS AND OTHER PROPRIETARY RIGHT

UNDP shall be entitled to all intellectual property and other proprietary rights including but not limited to patents, copyrights, and trademarks, with regard to products, or documents and other materials which bear a direct relation to or are produced or prepared or collected in consequence of or in the course of the execution of this Contract. At the UNDP's request, the Contractor shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring them to UNDP in compliance with the requirements of the applicable law.

12.	USE OF NAME, EMBLEM OR OFFICIAL SEAL OF UNDP OR THE UNITED NATIONS

The Contractor shall not advertise or otherwise make public the fact that it is a Contractor with UNDP, nor shall the Contractor, in any manner whatsoever use the name, emblem or official seal of UNDP or the United Nations, or any abbreviation of the name of UNDP or the United Nations in connection with its business or otherwise.

13.	CONFIDENTIAL NATURE OF DOCUMENTS AND INFORMATION

13.1	All maps, drawings, photographs, mosaics, plans, reports, recommendations, estimates, documents and all other data compiled by or received by the Contractor under this Contract shall be the property of UNDP, shall be treated as confidential and shall be delivered only to UNDP authorized officials on completion of work under this Contract.

13.2	The Contractor may not communicate at any time to any other person, Government or authority external to UNDP, any information known to it by reason of its association with UNDP which has not been made public except with the authorization of UNDP; nor shall the Contractor at any time use such information to private advantage. These obligations do not lapse upon termination of this Contract.

14.	FORCE MAJEURE; OTHER CHANGES IN CONDITIONS

14.1	Force majeure, as used in this Article, means acts of God, war (whether declared or not), invasion, revolution, insurrection, or other acts of a similar nature or force which are beyond the control of the Parties.

14.2	In the event of and as soon as possible after the occurrence of any cause constituting force majeure, the Contractor shall give notice and full particulars in writing to UNDP, of such occurrence or change if the Contractor is thereby rendered unable, wholly or in part, to perform its obligations and meet its responsibilities under this Contract. The Contractor shall also notify UNDP of any other changes in conditions or the occurrence of any event which interferes or threatens to interfere with its performance of this Contract. The notice shall include steps proposed by the Contractor to be taken including any reasonable alternative means for performance that is not prevented by force majeure. On receipt of the notice required under this Article, UNDP shall take such action as, in its sole discretion; it considers to be appropriate or necessary in the circumstances, including the granting to the Contractor of a reasonable extension of time in which to perform its obligations under this Contract.

14.3	If the Contractor is rendered permanently unable, wholly, or in part, by reason of force majeure to perform its obligations and meet its responsibilities under this Contract, UNDP shall have the right to suspend or terminate this Contract on the same terms and conditions as are provided for in Article 15, "Termination", except that the period of notice shall be seven (7) days instead of thirty (30) days.

15. TERMINATION

15.1 Either party may terminate this Contract for cause, in whole or in part, upon thirty days notice, in writing, to the other party. The initiation of arbitral proceedings in accordance with Article 16 "Settlement of Disputes" below shall not be deemed a termination of this Contract.

15.2 UNDP reserves the right to terminate without cause this Contract at any time upon 15 days prior written notice to the Contractor, in which case UNDP shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination.

15.3 In the event of any termination by UNDP under this Article, no payment shall be due from UNDP to the Contractor except for work and services satisfactorily performed in conformity with the express terms of this Contract. The Contractor shall take immediate steps to terminate the work and services in a prompt and orderly manner and to minimize losses and further expenditures.

15.4 Should the Contractor be adjudged bankrupt, or be liquidated or become insolvent, or should the Contractor make an assignment for the benefit of its creditors, or should a Receiver be appointed on account of the insolvency of the Contractor, UNDP may, without prejudice to any other right or remedy it may have, terminate this Contract forthwith. The Contractor shall immediately inform UNDP of the occurrence of any of the above events.

16.	 SETTLEMENT OF DISPUTES

16.1. Amicable Settlement

The Parties shall use their best efforts to settle amicably any dispute, controversy or claim arising out of, or relating to this Contract or the breach, termination or invalidity thereof. Where the parties wish to seek such an amicable settlement through conciliation, the conciliation shall take place in accordance with the UNCITRAL Conciliation Rules then obtaining, or according to such other procedure as may be agreed between the parties.

16.2. Arbitration

Unless, any such dispute, controversy or claim between the Parties arising out of or relating to this Contract or the breach, termination or invalidity thereof is settled amicably under the preceding paragraph of this Article within sixty (60) days after receipt by one Party of the other Party's request for such amicable settlement, such dispute, controversy or claim shall be referred by either Party to arbitration in accordance with the UNCITRAL Arbitration Rules then obtaining, including its provisions on applicable law. The arbitral tribunal shall have no authority to award punitive damages. The Parties shall be bound by any arbitration award rendered as a result of such arbitration as the final adjudication of any such controversy, claim or dispute.

17.	PRIVILEGES AND IMMUNITIES

Nothing in or relating to this Contract shall be deemed a waiver, express or implied, of any of the privileges and immunities of the United Nations, including its subsidiary organs.

18.	TAX EXEMPTION

18.1 Section 7 of the Convention on the Privileges and Immunities of the United Nations provides inter-alia that the United Nations, including its subsidiary organs, is exempt from all direct taxes, except charges for public utility services, and is exempt from customs duties and charges of a similar nature in respect of articles imported or exported for its official use. In the event any governmental authority refuses to recognize the United Nations exemption from such taxes, duties or charges, the Contractor shall immediately consult with UNDP to determine a mutually acceptable procedure.

18.2 Accordingly, the Contractor authorizes UNDP to deduct from the Contractor's invoice any amount representing such taxes, duties or charges, unless the Contractor has consulted with UNDP before the payment thereof and UNDP has, in each instance, specifically authorized the Contractor to pay such taxes, duties or charges under protest. In that event, the Contractor shall provide UNDP with written evidence that payment of such taxes, duties or charges has been made and appropriately authorized.

19.	CHILD LABOUR

19.1	The Contractor represents and warrants that neither it, nor any of its suppliers is engaged in any practice inconsistent with the rights set forth in the Convention on the Rights of the Child, including Article 32 thereof, which, inter alia, requires that a child shall be protected from performing any work that is likely to be hazardous or to interfere with the child's education, or to be harmful to the child's health or physical mental, spiritual, moral or social development.

19.2	Any breach of this representation and warranty shall entitle UNDP to terminate this Contract immediately upon notice to the Contractor, at no cost to UNDP.

20.	OBSERVANCE OF THE LAW

The Contractor shall comply with all laws, ordinances, rules, and regulations bearing upon the performance of its obligations under the terms of this Contract.

21.	AUTHORITY TO MODIFY

No modification or change in this Contract, no waiver of any of its provisions or any additional contractual relationship of any kind with the Contractor shall be valid and enforceable against UNDP unless provided by an amendment to this Contract signed by the authorized official of UNDP.

TERMS OF REFERENCE

PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS _______________________________________________________________________________________

- BACKGROUND  TO THE UNDP PROGRAMME

In April 2010 United Nations Development Programme (UNDP) and the Government of Uganda (GOU) endorsed the Country Programme Action Plan (CPAP) 2010 -2014.  The CPAP is a five year framework defining mutual cooperation between the GoU and UNDP. The CPAP is aligned to GoU’s National Development Plan (NDP), as well as the United Nations Development Assistance Framework (UNDAF 2010-2014).  It is nationally executed through the Ministry of Finance Planning and Economic Development (MFPED).

The country programme has two main components which are Accountable Democratic Governance (ADG) and Growth and Poverty Reduction (GPR).    Further, through the two programme components UNDP is contributing to the Northern Uganda recovery priorities set forth in the Peace Recovery and Development Plan (PRDP) and is focused on specific CPR outputs namely:

- Functional firearms registries and stockpile management and destruction systems in place.

- Policy and mechanisms for peace-building, reconciliation and reintegration in place.

Two (2) targeted project documents shall be prepared to guide delivery.

- BACKGROUND TO THE PROPOSED PROJECTS

Northern Uganda has been faced with 20-years of armed insurgence that led to proliferation of arms, destruction of the region’s economic base and breakdown in social cohesion among communities.  Insecurity in the Karamoja sub-region, partly rooted in the proliferation of small arms and problematic disarmament programmes, has hampered administration of central government services resulting in chronic breakdown of law and order and under development.  At the root of this insurgency lie issues of inequality, exclusion from state mechanisms and development opportunities, which have marginalized a large proportion of vulnerable groups, the poor in general and overall led to low growth and income for the region as compared with other regions in the country.  61% of the population in the North and 80% in the Karamoja region are living below the poverty line, compared to 30% at national level.  These withstanding, high incidences of intertwined conflicts in northern Uganda have witnessed a tremendous increase in the number of agencies working on peace building and conflict issues in northern Uganda.  As such a fundamental challenge is also to ensure that the crisis prevention, peace building and recovery activities in the region are coordinated within the Government Peace, Recovery, and Development Plan - which provides a strategic framework for Northern Uganda for the short term.

In view of the above background, through  output 1.2.2: Functional Firearms Registries and Stockpile Management and destruction Systems in Place; UNDP will support Uganda National Focal Point (NFP) in implementing its mandate on disarmament, destruction of firearms and updating of firearm database as well as undertaking advocacy.  In addition, support will be provided for policy advocacy for the ratification of the Protocol on the Prevention, Combating and Eradication of Cattle Rustling in Eastern Africa as a counter measure to the proliferation of illicit small arms and light weapons.  Under Output 1.2.3: Policy and mechanisms for peace-building, reconciliation and reintegration in place; UNDP will contribute to the prevention of the recurrence of armed conflicts, supporting peace building and reconciliation.  In this regard focus will be placed on support to: i) Finalization of the Peace Policy; ii)Strengthening the National Platform on Peace building for improved coordination; iii) Development of Local Government capacity for mediation, conflict management, and conflict responsive planning; iv) cross-border(national, tribal) peace-building initiatives; Intercommunity/clan peace building initiatives; and ii) Support to community groups and traditional/cultural structures for promoting dispute resolution and building peace and reconciliation.

It is envisaged that the two projects will ultimately contribute to the realization of CPAP outcome 1.2: Selected institutions capacitated to deliver community security and access to justice services.  Each output will be delivered through one project document:

| CPAP Output | Potential Implementing partner |
| --- | --- |
| Output 1.2.2 Functional Firearms Registries and Stockpile Management and destruction System in place | Ministry of Internal Affairs (Uganda National Focal Point Department) |
| Output 1.2.3 Policy and mechanisms for peace-building, reconciliation and reintegration in place | Office of the Prime Minister Ministry of Internal Affairs |

- OBJECTIVES

- Identify UNDP areas of comparative advantage in the areas of Small Arms Control and Peace Building, within the broader framework of the CPAP 2010-2014 and UNDAF 2010-2014.

- Identify programmatic strategic interventions that will contribute to:

- A functional registry system for Firearms, Stockpile Management and destruction; and

- Policy and mechanisms for peace-building, reconciliation and reintegration.

- Undertake the initial identification and assessment of the project risks.

- Prepare 2 project documents that will guide the implementation and delivery of the selected programmatic interventions.

- SCOPE OF WORK

The preparation of the project documents shall commence with a project formulation exercise.  This will involve identification of UNDPs niche and thus enable the articulation of conceptual and operational linkages of the outcome and outputs (i.e. show how the outputs in combination contribute to the outcomes over the 4 year period).  Based on the niche, the specific interventions and strategies shall be firmed up, as well as ensuring clear articulation of indicators, baselines, targets, activities and actions. It will also inform selection of the implementing partner and collaborating partners for delivering on the output.  To ensure project quality, the project formulation will build on lessons learnt during the implementation of CPAP 2006-2010, stakeholder participation and partnership building; managing for results and reporting.  The project documents will be used as the tool to guide efficient project management and for resource mobilization.  It will be developed based on UNDP Project Document template and will reflect the following aspects:

- Continuity over the four(4) year period of the CPAP;

- Elaboration of specific deliverables and activities to be implemented to achieve those deliverables, with clear time lines and benchmarks.  It will be  important to determine the timeframe within which the different components will be delivered; and at which point the project should be closed;

- Elaboration of synergies within the governance and poverty programme Components and across the CPAP (2010-2014) as well as other similar programmes/projects;

- Annualized work plans for the project duration with clear indication of responsible parties/partners

- Integration of cross cutting issues including human rights based approach to programming; and the contribution to gender responsiveness. The project document should clearly show activities that will contribute to these cross cutting issues.

- Clear monitoring and evaluation strategy;

- Analysis and articulation of how best placed the proposed implementing partners are to implement the project e.g. based on mandate and capacity to act;

- Clear partnership/collaboration strategy, by elaborating on the responsibilities of UNDP, the implementing partner and the collaborating partner;

- State the composition of the project board as well as the terms of reference for the board; and

- Risks and how they can be mitigated; and

- Clear exit strategy.

- TASKS/ACTIVITIES

- Attend detailed joint briefing by the UNDP and MFPED/ALD on programming and clarification of expectations – one day after issuance of the contract.

- Prepare and submit Inception Report to UNDP and MFPED/ALD.

- Present inception report and discussion guide for consideration by UNDP and MFPED/ALD prior to wider consultations.

- Gather and analyze information to inform project document formulation.

Review critical documentation/literature related to or that informs the UNDP programming, such as: The Government’s National Development Plan; United Nations Development Assistance Framework (UNDAF) 2010/2014, CPAP document 2010/2014, Peace, Recovery and Development Plan (PRDP), Karamoja Integrated Disarmament and Development Programme (KIDDP); United Nations Peace Building and Recovery Assistance Programmed( UNPRAP), the report on the Assessment of development results Uganda, September 2009, project review reports, project evaluation reports, etc.

- In reviewing the documentation ensure that those aspects of ongoing projects (e.g. Crisis Management Recovery Project) that are also covered in the CPAP 2010-2014 to inform the new project documents.

- Undertake thorough consultations within UNDP Uganda, and with key stakeholders from UN agencies, Government, NGOs, CSOs, development partners, District representatives - to elicit and interrogate information that would inform the project document formulation and define all aspects of the project document.

- Noting that CPR is a cross cutting issue, ensure that CPR issues are addressed in the respective project documents of the country programme.

- Project document drafting and finalization

- Submit draft project document based on the UNDP project document template.

- Conduct quality assurance of the prepared project documents – based on the quality assurance templates that will be shared with the consultants during the initial briefing.

- Present draft project document to pre Project Appraisal Committee (PAC) meeting prior finalization of project document – that should involve the UNDP office staff and selected resource persons.

- Completion of draft final project documents taking into consideration comments arising from the validation pre PAC meeting.

- Prepare briefing and present draft final project documents to the PAC meeting for endorsement.

- Complete and submit final project documents- ready for signature.

NB: Documents submitted should be both in softcopy form (Microsoft office word 2007) and 2 hard copies.

- DELIVERABLES

| Item | When | Key issues to take into consideration |
| --- | --- | --- |
| - Inception report | 7th days after issuance of contract | Response to the terms of reference: understanding, interpretation and constructive comments. Methodology and instruments of carrying out the assignment Work plan and implementation schedule. |
| - Draft project documents(2) | 14th day after inception report. | The project documents should be prepared based on the UNDP project document template To be informed by national level consultations and consultations with stakeholders. |
| - Pre- Project Appraisal Committee (PAC) briefing/presentation | Half day pre PAC meeting - 4th day after submission of draft project documents | Involving UNDP staff, to validate the project document and recommend for finalization. |
| - Final draft project documents(3) | 4th day after the pre PAC meeting | To incorporate comments arising from the pre PAC meeting. |
| - Briefing and presentation of final draft project documents to the PAC meeting. | 4th day after the pre PAC meeting | Involving members of the outcome board, to validate and endorse the project documents. |
| - Final project documents (ready for signature) | 4th day after the PAC meeting | Finalization of project documents, ensuring that they are ready for signature. |

- TIMING AND DURATION

The assignment is expected to take approximately 30 working days starting in December 2010.

- REPORTING ARRANGEMENTS

The consultants will work closely with the UNDP Crisis Prevention and Recovery unit (that also includes the UNDP Northern Uganda Sub-Offices) and implementing partners – most notably, the Office of the Prime Minister, Ministry of Internal Affairs and selected District Local Governments.

The consultants will report to and be accountable to the UNDP Team Leader for Crisis Prevention and Recovery and overall technical advisory support of Senior Recovery Advisor.  They will work under the overall guidance and leadership of the Country Director, and the UNDP Resident Representative.  They will liaise on a day to day basis with the programme consultant.

At the conclusion of each deliverable, there will be a presentation to Senior Management in UNDP for guidance.

Towards the end of the assignment a pre PAC meeting and PAC meeting will be conducted and relevant comments and suggestions be appropriately incorporated in the final project documents.

- PROFILE OF THE FIRM

A national/international consultancy firm/institution is required to undertake development of Crisis Prevention and Recovery (CPR) project documents.  The consultancy firm/institution should provide three (3) international consultants as follows:

- Small Arms Control  Expert

- Conflict resolution/Peace building Expert

- Human Rights/Gender expert - with experience in post  conflict  programming

The experts should have:

- Minimum Masters Degree in the area of expertise (areas are indicated above).

- Minimum of 10 years working experience in formulation and design of programmes and project documents in the respective area of specialization.

- Strong knowledge about the development context of Uganda and northern Uganda.

- Capacity for strategic thinking.

- Excellent analytical skills.

- Excellent communication and writing skill in English writing.

- Strong task management competency.

- Strong team work skill

- Knowledge of UNDP Programming will be an advantage.

- APPLICATION PROCEDURE

The technical proposal should include:

- Detailed curriculum vitae (CV) of the consultancy team members who will consistently work on the assignment until its finalization.

- Two samples of previous project documents designed; indicating the agency or institution for which it was designed.

Annex IV

PROPOSAL SUBMISSION FORM

Dear Sir / Madam,

Having examined the Solicitation Documents, the receipt of which is hereby duly acknowledged, we, the undersigned, offer to provide services for the “PREPARATION OF PROJECT DOCUMENTS FOR CRISIS PREVENTION AND RECOVERY PROJECTS” the sum as may be ascertained in accordance with the Price Schedule attached in a separate envelope from the technical proposal and submitted as part of this Proposal. We undertake, if our Proposal is accepted, to commence and complete all implementation of projects specified in the contract within the time frame stipulated. We agree to abide by this Proposal for a specified period from the date fixed for opening of Proposals in the Request for Proposal, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

We understand that you are not bound to accept any Proposal you may receive.

Dated this day /month of year

F. Signature

(In the capacity of)

Duly authorized to sign Proposal for and on behalf of

Annex V

PRICE SCHEDULE

The Contractor is asked to prepare the Price Schedule as a separate envelope from the rest of the RFP response as indicated in Section D paragraph 14 (b) of the Instruction to Offerors.

All prices/rates quoted must be exclusive of all taxes, since the UNDP is exempt from taxes as detailed in Section II, Clause 18.’

The Price Schedule must provide a detailed cost breakdown. Provide separate figures for each functional grouping or category.

Estimates for cost-reimbursable items, if any, such as travel, and out of pocket expenses should be listed separately.

In case of an equipment component to the service provided, the Price Schedule should include figures for both purchase and lease/rent options. UNDP reserves the option to either lease/rent or purchase outright the equipment through the Contractor. The format shown on the following pages should be used in preparing the price schedule. The format includes specific expenditures, which may or may not be required or applicable but are indicated to serve as examples. In addition to the hard copy, if possible please also provide the information on CD/Flash Drive.

| Price Schedule Request for Proposals for Service |  |  |  |  |
| --- | --- | --- | --- | --- |
| Description of Activity |  | Number of Staff | G. Monthly Rate | Estimated Amount |
| 1 | Remuneration |  |  |  |
| 1.1 | Services in Home office |  |  |  |
| 1.2 | Services in field |  |  |  |
| 2 | Out of Pocket Expenses |  |  |  |
| 2.1 | Travel |  |  |  |
| 2.2 | Per Diem Allowances |  |  |  |
| 2.3 | Communications |  |  |  |
| 2.4 | Reproduction and Reports |  |  |  |
| 2.5 | Equipment and other items |  |  |  |

An outcome is an intended or achieved short-term to medium-term effects of an intervention. It describes the intended changes in development conditions resulting from programme/project interventions. It relates to changes in institutional performance or behavior of individuals or groups. It also represents changes in development conditions, which occur between the completion of outputs and the achievement of impact.

Project titles/names to be firmed up during the process of project design.

Indicators tell us how intended results will be measured, and whether (or how far) these results have been achieved. Indicators are quantitative or qualitative variables that allow the verification of changes provided by a development intervention relative to what was planned.

Baselines establish the value of the indicator at the beginning of the planning period.

Targets describe expected values upon completion of the plan.

Activities are actions taken or work performed through which inputs, such as funds, technical assistance and other resources are mobilized to produce specific outputs.

For each project there will be one implementing partner, the project formulation shall inform the firming up of the most suitable Implementing Partner and the collaborating partners.

The UNDP project document template will be shared with the consultants during the initial briefing.